## Sheet1
TEMPUS IV - Third Call for proposals, 9 March 2010 | [25 empty] | Development | [6 empty] | DEV |  |  | Table 1
[26 empty] | Quality Plan | [6 empty] | QPLN
| WORKPLAN & WORKPACKAGES | [24 empty] | Dissemination | [6 empty] | DISS
| Please ensure that the information you provide in this worksheet is consistent with Part F of your eForm | [24 empty] | Exploitation | [6 empty] | EXP
[26 empty] | Management | [6 empty] | MNGT
The same reference and sub-reference numbers used in the logical framework matrix must be assigned to each deliverable and related activity. The first month of the project must be marked 1. Please use the following symbols: - Activity carried out in the EU or Candidate Country: O - Activity carried out in the Partner Country: X
WP Type | Deliverable / Activity Ref. N° | Activities (as indicated in the LFM) | Dura- tion (weeks) | Month
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
DEV | Act. 1.1 | Project start up activities and kick-off meeting | 4 | bar: Month 1 to Month 2
DEV | Act. 1.2 | Mapping of the current curricula and programs in Serbia | 9 | bar: Month 2 to Month 4
DEV | Act. 1.3 | Benchmarking analysis of similar programmes in EU organizations | 9 | bar: Month 2 to Month 5
DEV | Act. 1.4 | Research visits to EU to gain first-hand knowledge on TE programs | 4 | bar: Month 4 to Month 5
DEV | Act. 1.5 | Drafting of a report containing recommendations/findings | 3 | bar: Month 6
DEV | Act. 1.6 | Project workshop in Novi Sad | 1 | bar: Month 7
DEV | Act. 2.1 | Revising and adopting teacher competences by Serbian authorities | 3 | bar: Month 7 to Month 8
DEV | Act.2.2 | Elaboration of procedures for issuing teacher certificates and approval of TE programs | 5 | bar: Month 8 to Month 10
DEV | Act. 2.3 | Adding an approved profile of a master subject teacher | 3 | bar: Month 8 to Month 10
DEV | Act. 2.4 | Elaboration of procedures for ensuring that programme courses can be recognized | 5 | bar: Month 8 to Month 10
DEV | Act. 2.5 | Elaboration of procedures on cooperation of universities, school and authorities regarding school practice | 4 | bar: Month 10 to Month 13
DEV | Act. 2.6 | Legislation tuning and developing | 5 | bar: Month 10 to Month 15
DEV | Act. 3.1 | Agreement on a CD workplan during the workshop in Novi Sad | 1 | bar: Month 7
DEV | Act. 3.2 | Developing program and course learning outcomes and ECTS | 6 | bar: Month 7 to Month 10
DEV | Act. 3.3 | Drafting of curricula, development of main course contents and teaching materials | 14 | bar: Month 10 to Month 15
DEV | Act. 3.4 | Selection of teachers to be involved in the Master and retraining mission to EU | 3 | bar: Month 10 to Month 12
DEV | Act. 3.5 | Workshop on Master curriculum design in Nis | 1 | bar: Month 15
DEV | Act. 3.6 | Finalisation of Curricula on the basis of workshop outcomes | 2 | bar: Month 15
DEV | Act. 3.7 | Submission of curricula for accreditation | 2 | bar: Month 15 to Month 16
DEV | Act. 3.8 | Web publishing of updated teaching materials | 1 | bar: Month 15; Month 19; Month 23; Month 27; Month 31; Month 35
DEV | Act. 4.1 | School practice development work plan agreed in occasion of workshop planned | 1 | bar: Month 7
DEV | Act. 4.2 | Developing a model of school practice | 4 | bar: Month 8 to Month 9
DEV | Act. 4.3 | Establishment of criteria for school selection and estimation of school capacities | 3 | bar: Month 10
DEV | Act. 4.4 | Selection and formal engagement of schools performed | 2 | bar: Month 11
DEV | Act. 4.5 | Re-education teachers in primary and secondary schools for mentorship role | 12 | bar: Month 12 to Month 15
DEV | Act. 5.1 | Definition of tender specifications and procurement procedures | 1 | bar: Month 7
DEV | Act. 5.2 | Purchase of materials and installation of equipment | 1 | bar: Month 15
QPLN | Act. 6.1 | Mapping of the Quality Assurance mechanisms | 6 | bar: Month 7 to Month 12
QPLN | Act. 6.2 | Drafting of courses evaluation questionnaires | 2 | bar: Month 13
QPLN | Act. 6.3 | Distribution of evaluation questionnaire to students and elaboration or results | 8 | bar: Month 16; Month 22; Month 29; Month 36
DEV | Act. 7.1 | Students' selection and enrolments | 4 | bar: Month 14; Month 26
DEV | Act. 7.2 | Implementation of the courses | 54 | bar: Month 16 to Month 33
DEV | Act. 7.3 | Seminars of EU academic staff | 4 | bar: Month 24 to Month 25; Month 30 to Month 31
DEV | Act. 7.4 | Internships of MA students to partners' institutions | 4 | bar: Month 24 to Month 29
DISS | Act. 8.1 | Planning of the dissemination activities | 1 | bar: Month 2
DISS | Act. 8.2 | Setting up and maintenance of the project web site | 16 | bar: Month 1 to Month 4; Month 11 to Month 14; Month 23 to Month 26; Month 33 to Month 36
DISS | Act. 8.3 | Issuing of regular project newsletter | 6 | bar: Month 6; Month 12; Month 18; Month 24; Month 30; Month 36
DISS | Act. 8.4 | Issuing of press releases | 4 | bar: Month 2 to Month 3; Month 11 to Month 12; Month 14 to Month 15; Month 21 to Month 22; Month 27 to Month 28; Month 35 to Month 36
DISS | Act. 8.5 | Production of Students' guides | 6 | bar: Month 12; Month 24
DISS | Act. 8.6 | Organisation of mid-term international dissemination conferences | 3 | bar: Month 7; Month 14; Month 25
DISS | Act. 8.7 | Info days for students | 2 | bar: Month 14; Month 25
DISS | Act. 8.8 | Final project conference | 1 | bar: Month 35 to Month 36
MNGT | Act. 9.1 | Organization of the kick-off meeting and appointments of members to sit in MB | 1 | bar: Month 2
MNGT | Act. 9.2 | Drawing up of the handbook on project management | 4 | bar: Month 1 to Month 6
MNGT | Act. 9.3 | Project monitoring | 72 | bar: Month 1 to Month 36
MNGT | Act. 9.4 | Project reporting | 72 | bar: Month 17 to Month 20; Month 33 to Month 36
EXP | Act. 10.1 | Implementation of modernized curricula also after the end of the project | N/A | bar: Month 14; Month 36
EXP | Act. 10.2 | Ensuring students enrolments also after the end of the project | N/A | bar: Month 13; Month 25; Month 36
EXP | Act. 10.3 | Appropriate feed-back mechanism to measure students' satisfaction maintained | N/A | bar: Month 16; Month 36
EXP | Act. 10.4 | Arrangements to keep operational the on-line platform for on-line publishing of teaching materials | N/A | bar: Month 15; Month 27; Month 36
EXP | Act. 10.5 | Mantaining links between Serbian universities, school and relevant authorities | N/A | bar: Month 10; Month 15; Month 22; Month 34